## Sheet1
Wifi Internet Controlled Hydraulic Scissor Lifter Model Project Bar chart
SNo. | Activity | Start Date | End Date | Duration | Status | 2024-04-12 | 2024-04-13 | 2024-04-14 | 2024-04-15 | 2024-04-16 | 2024-04-17 | 2024-04-18 | 2024-04-19 | 2024-04-20 | 2024-04-21 | 2024-04-22 | 2024-04-23 | 2024-04-24 | 2024-04-25 | 2024-04-26 | 2024-04-27 | 2024-04-28 | 2024-04-29 | 2024-04-30 | 2024-05-01 | 2024-05-02 | 2024-05-03 | 2024-05-04 | 2024-05-05 | 2024-05-06 | 2024-05-07 | 2024-05-08 | 2024-05-09 | 2024-05-10 | 2024-05-11 | 2024-05-12 | 2024-05-13 | 2024-05-14
1 | Identification of a problem or Need | 2024-04-12 | 2024-04-13 | 2 | Completed | Completed | Completed
2 | Synopsis and Project Selection | 2024-04-13 | 2024-04-14 | 2 | Completed |  | Completed | Completed
3 | Research and Understanding | 2024-04-15 | 2024-04-17 | 3 | Completed |  |  |  | Completed | Completed | Completed
4 | Design and Planning | 2024-04-17 | 2024-04-19 | 3 | Completed | [5 empty] | Completed | Completed | Completed
5 | Materials and Resource Procurements | 2024-04-20 | 2024-04-24 | 5 | Completed | [8 empty] | Completed | Completed | Completed | Completed | Completed
6 | Assembly and Fabrication | 2024-04-23 | 2024-04-29 | 7 | Completed | [11 empty] | Completed | Completed | Completed | Completed | Completed | Completed | Completed
7 | Integration of IoT | 2024-04-28 | 2024-05-04 | 7 | Completed | [16 empty] | Completed | Completed | Completed | Completed | Completed | Completed | Completed
8 | Calibration and Testing | 2024-05-03 | 2024-05-07 | 5 | Completed | [21 empty] | Completed | Completed | Completed | Completed | Completed
9 | Instructions and Documentations | 2024-04-17 | 2024-05-11 | 25 | Completed | [5 empty] | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed
10 | Feedbacks and Improvements | 2024-05-11 | 2024-05-12 | 2 | Completed | [29 empty] | Completed | Completed